## Sheet1
Component | Process | Details | Documents | Vendor | Cost (qty 10) | Cost (qty 100) | Turnaround
Chassis | Purchase | Hammond Mfg Part Number 1444-9 |  | Digikey www.digikey.com 800-346-6873 | 82.2 | 822 | 1 week
Chassis | Modification | Cut in half. Drill and tap holes. | drawing: pm-chassis.pdf | - | 0 | 0 | -
PCB | Fabrication | 4 layers, 2-sided solder mask, 2-sided silkscreen, 1oz FR4 | gerber drawings | Sunstone Circuits www.sunstone.com 800-228-8198 | 673 | 1356.9 | 1 week
Components | Purchase | FT232RL and 20-pin connectors | pm-compm.pdf | Mouser www.mouser.com 800-346-6873 | 149.76 | 1497.6 | 1 week
Components | Purchase | everything else | pm-compd.pdf | Digikey www.digikey.com 800-346-6873 | 712.41 | 7124.1 | 1 week
PCB | Assembly |  | pm-bom.xlsx pm-centroid gerber drawings | Screaming Circuits www.screamingcircuits.com 866-784-5887 | 971.41 | 3500 | 2 weeks | ?
Cable | Assembly |  | pm-cablea.pdf pm-cableb.pdf | TLC Electronics a.williams@tlcelectronics.com www.tlcelectronics.com 561-558-2570 | 1021 | 10210 | 3 weeks | (?)
PCB | Programming | AVR Dragon probably the best option | firmware and programming scripts | - | 0 |  | -
PCB | Validation |  | script? Procedure? | - | 0 |  | -
[5 empty] | 361 | 245