## Sheet1
Component	Process	Details	Documents	Vendor	Cost (qty 10)	Cost (qty 100)	Turnaround
Chassis	Purchase	Hammond Mfg Part Number 1444-9		Digikey / www.digikey.com / 800-346-6873	$82.20	$822.00	1 week
Chassis	Modification	Cut in half. Drill and tap holes.	drawing: pm-chassis.pdf	-	$0.00	$0.00	-
PCB	Fabrication	4 layers, 2-sided solder mask, 2-sided silkscreen, 1oz FR4	gerber drawings	Sunstone Circuits / www.sunstone.com / 800-228-8198	$673.00	$1,356.90	1 week
Components	Purchase	FT232RL and 20-pin connectors	pm-compm.pdf	Mouser / www.mouser.com / 800-346-6873	$149.76	$1,497.60	1 week
Components	Purchase	everything else	pm-compd.pdf	Digikey / www.digikey.com / 800-346-6873	$712.41	$7,124.10	1 week
PCB	Assembly		pm-bom.xlsx / pm-centroid / gerber drawings	Screaming Circuits / www.screamingcircuits.com / 866-784-5887	$971.41	$3,500.00	2 weeks	?
Cable	Assembly		pm-cablea.pdf / pm-cableb.pdf	TLC Electronics / a.williams@tlcelectronics.com / www.tlcelectronics.com / 561-558-2570	$1,021.00	$10,210.00	3 weeks	(?)
PCB	Programming	AVR Dragon probably the best option	firmware and programming scripts	-	$0.00		-
PCB	Validation		script? Procedure?	-	$0.00		-

					$361.00	$245.00